# Hosted Tables Program — Manager Handoff

For: Whoever takes over day-to-day management of the Hosted Tables Program from Mike Harrigan. Last updated: 2026-04-29

Read this first. For deeper detail, see docs/hosted-tables-program.md (full spec) and docs/website-design-conventions.md (visual / design language).

## 1. What the program is

A named-group dining experience for Statesman's Concierge Pass holders at the Countdown 250 Ball (Washington Hilton, July 3, 2026).

Statesman's Pass holders can either host a group ("Hosted Table") or join an existing one. Each table is a "Party Inside the Party" inside the Statesman's Concierge Area. We do all the logistics. The host gets public recognition.

Two tiers:

| Tier | Threshold | Benefits |
| --- | --- | --- |
| Hosted Table | Any size (2+) | Reserved table together · Host named in event program · Host named on website |
| Featured Hosted Table | 6+ guests | Above + Public "Toast to the Hosts" + Personalized table signage |

There is no extra cost to host or to join — every member just buys their own Statesman's Pass.

## 2. Program goals

Primary: Drive Statesman's Pass sales by giving people a structured way to recruit their network. Each host is essentially a recruiting agent.

Secondary:

Web traffic / SEO — every host shares the /hosted-group-tables URL with their guests, driving organic visits to our site

Social proof — public roster shows the program is alive and growing; helps fence-sitters convert

Affinity targeting — anchor tables (alumni, professional groups, family reunions) attract buyers who don't know anyone but want to join their tribe

## 3. Critical success factors

### A. The "don't dissuade" rule (most important)

Mike was clear: the program must NEVER feel like pressure. Three messages must always come through:

Buying tickets together = seated together automatically. No formal group needed.

Hosting and joining are completely optional. A solo Statesman's Pass works perfectly.

Don't want to host? Either join an affinity table OR be seated with other distinguished guests in the Statesman's Concierge Area.

The page handles this with a "Three Ways to Enjoy Your Statesman's Pass" triptych. Do not let copy edits accidentally erode this messaging. Future ad campaigns, emails, and FAQ revisions should always reinforce these three points.

### B. Common pitfalls to actively avoid

| Pitfall | Symptom | Mitigation |
| --- | --- | --- |
| "I have to bring a big group" | People hesitant to host | Lead with "any size 2+ qualifies." 6+ is the bonus tier, not the entry. |
| "There's an extra charge" | Buyers question the value | "No cost to you or your guests" is on the homepage CTA, the page, the FAQ. Don't bury it. |
| "I have to commit before knowing my guest count" | Hosts won't even start | Form takes 30 seconds. No financial commitment. Drop out anytime. |
| "I'm alone, I can't go to this event" | Solo buyers feel awkward | Option 3 in the Three Ways triptych must always read first-class, not consolation prize. |
| Slowing down checkout with group questions | Cart abandonment | We deliberately do NOT use Eventbrite custom questions. People learn about the program post-purchase. |

### C. Other success factors

Speed of host onboarding. The form must stay short and approval should be same-day where possible. Friction here = dropouts.

Honesty on the public roster. Counts shown are the truth (seeds + real signups). Never inflate visible names beyond what was actually submitted with consent.

Communication to hosts. A host who fills the form and hears nothing for a week loses momentum. Confirmation should go out within 24 hours.

Deadline visibility. T-60 / T-30 / T-7 dates are on the page. They drive urgency. Don't soften them.

## 4. What's already done

| Item | Where |
| --- | --- |
| /hosted-group-tables page rewrite (full design + copy) | src/pages/hosted-group-tables.astro |
| Live roster of 9 seed tables (66 seeded members total) | src/data/hosted-groups.ts |
| Homepage Hosted Tables section with gold-on-navy treatment | src/pages/index.astro |
| Statesman ticket card with "Host your Own Party Inside the Party" gold CTA | src/pages/index.astro |
| Audit script with 6 guardrails (image existence, routes, anchors, IDs, carousels, dead imports) | scripts/audit_assets.py |
| Production deadline framing (T-60 / T-30 / T-7) | Embedded in page copy |
| "Three Ways to Enjoy Your Statesman's Pass" reassurance section | Embedded in page |
| FAQ block on the page (6 questions, including the don't-dissuade ones) | Embedded in page |

## 5. What's left to do before launch

| # | Item | Owner | Notes |
| --- | --- | --- | --- |
| 1 | Create two Google Forms (Create-Hosted-Table + Join-Hosted-Table) | Manager | Field specs in docs/hosted-tables-program.md §"The two Google Forms" |
| 2 | Replace placeholder URLs in src/pages/hosted-group-tables.astro with real Form URLs | Manager | Constants CREATE_FORM_URL and JOIN_FORM_URL at top of file. Both currently fall back to mailto:CountdownAmerica250@gmail.com. |
| 3 | Edit Eventbrite Statesman tier "additional info / thank you" to include program description | Manager | Draft text exists in chat history; available on request |
| 4 | Build "Hosted Tables Master" Sheet (the Form-receiving spreadsheet) with two views: (a) full-data, Mike-only and (b) public-display-only filter | Manager | All Form responses → master Sheet → public columns surface to roster |
| 5 | Draft host confirmation email + sample host-to-guest invitation email | Pending | Templates pending — Claude can draft on request |
| 6 | Update the Join Form's group dropdown to mirror the live roster (initial: 9 seed tables; add real groups as they're created) | Manager | ~30 sec per addition. Optional: install free formRanger Google Forms add-on for auto-sync from Sheet |

## 6. Ongoing operations (regular cadence)

| Cadence | Task |
| --- | --- |
| Daily (5 min) | Check Eventbrite for new Statesman's Pass purchases. Watch for incoming Forms. Reply to host inquiries within 24 hours. |
| Weekly (15 min) | Sync Form submissions → public roster. Update src/data/hosted-groups.ts counts (or names if any new ones consented to public listing). Push the change. New table created? Add it to the Join Form dropdown. |
| Weekly (10 min) | Brief check-in with each host whose group is filling — quick "you've got X confirmed, Y to reach Featured" email. Keeps momentum. |
| Monthly | Brainstorm 1–2 new affinity table themes that could attract buyers (e.g., professional networks, civic associations). Add them as seeded tables if they fit. |
| Monthly | Review FAQ + page copy against actual buyer questions received. If 3+ people ask the same thing, add it to the FAQ. |
| Monthly | Sales-channel brainstorm: which host or affinity table can be amplified via partner outreach, social, email blast, etc.? |
| At deadlines (T-60 / T-30 / T-7) | Hard cutoffs for program-print, signage, seating. Email all uncommitted hosts a week before each deadline. |

## 7. The technical touchpoints

| Asset | Path | Who edits |
| --- | --- | --- |
| Live roster data | src/data/hosted-groups.ts | Manager (weekly) |
| Page copy | src/pages/hosted-group-tables.astro | Manager (when copy changes are needed) |
| Homepage Hosted Tables section | src/pages/index.astro (search "hosted-tables" for section start) | Manager (rare) |
| Pre-deploy audit | scripts/audit_assets.py — run with python scripts/audit_assets.py | Manager (every push) |
| Deployment | GitHub Actions auto-deploys on push to main. ~60–90 sec to live. | Automatic |
| Repo URL | https://github.com/mikey-harrigan/countdown250 | — |

Standing rules:

Run python scripts/audit_assets.py before every push. All 6 guardrails must pass.

Never strip class="eventbrite-checkout" or ?aff=websitemain query param from any ticket-purchase link — they're required for the checkout integration and affiliate tracking.

Never expose private Form data (emails, order #s, phone) on the public roster.

The /statesmans-pass page exists at the URL but is currently unlinked from the homepage — preserved for future per-tier detail pages.

## 8. Where to dig deeper

`docs/hosted-tables-program.md` — Full program spec. Every decision and the reasoning behind it. The 9 seed tables. Both Google Form specs. Mike's full TODO list.

`docs/website-design-conventions.md` — Color terminology (Mike's specific usage of "navy blue" / "white" / etc.), section bg map, recurring patterns, what's been removed and shouldn't come back.

`C:\Users\USER\claude-backups\2026-04-29\` — Mirror of the docs above, plus a session-summary recapping the design session that produced this program.

## TL;DR for a busy manager

Read the page at `/hosted-group-tables`. That tells you what the program is and how it's marketed.

Build the two Google Forms and replace the two URLs in src/pages/hosted-group-tables.astro. That's the main launch blocker.

Watch the Forms inbox + Eventbrite. Update the roster weekly.

Protect the don't-dissuade messaging in any future copy edits.

When in doubt, run the audit before pushing.