# The Hosted Tables Program — Program Spec & Recovery Doc

Last updated: 2026-04-29 Purpose: Single source of truth for the Hosted Tables Program design, operational mechanics, and pending deliverables. Hand this to any future Claude session to restore context.

## Strategic context

Goal: Drive Statesman's Concierge Pass sales by giving people a structured, low-friction way to recruit their network into a "Party Inside the Party" at the event.

Mechanic: Hosts get peacocking benefits (named in program/website, public toast, signage). Guests buy their own Statesman's Pass and join the host's table. Mike (the operator) handles all the logistics.

Why it works: Aligns incentives — host gets credit, guest gets a curated experience, Mike gets the sales lift.

Cannibalization risk acknowledged: Some "groups" may just be friends who would have bought anyway. Mitigated by the Featured threshold (6+ for full benefits) — drives genuine recruiting.

## Naming conventions (LOCKED)

| Term | Use |
| --- | --- |
| The Hosted Tables Program | The operational name. Page headers, FAQ, navbar links, anywhere clarity matters. |
| "Party Inside the Party" | The experience descriptor. Headlines, marketing taglines, social copy. Used inline ("Host your own Party Inside the Party"). |
| Host | The role — the person organizing a Hosted Table |
| Guest | The role — anyone joining a host's table |
| Hosted Table | Any group of 2+, full base benefits |
| Featured Hosted Table | Group of 6+ (host + 5 guests), gets toast + signage |
| Open Affinity Table | Internal name for the seeded affinity tables (alumni, healthcare, etc.) — these have no named host; visitors see them as regular Hosted Tables in the public roster |

## The 2-tier benefits ladder

Decided after Mike pushed back on the original "minimum 6" proposal. Logic: small groups still get marketing-relevant recognition (zero marginal cost to us). Production-cost benefits gate at 6+.

### Hosted Table — any size (2+)

Reserved private table inside the Statesman's Concierge Area

Host named in the official event program

Host named on the event website

We handle every detail — host enjoys their party

### Featured Hosted Table — 6+ guests (host + 5)

Everything in Hosted Table, plus:

Public "Toast to the Hosts" ceremony at the event

Personalized table signage with host name & group name

Premium recognition during stage announcements

## Production deadlines

| Date | Event |
| --- | --- |
| T-60 days (~early May 2026) | Official event program goes to print. Hosts confirmed by this date are named in the printed program. |
| T-30 days | Personalized table signage cuts off (Featured Hosted Tables must finalize details by here). |
| T-7 days | Final seating chart locked. |

## The 9 seed tables (live roster at launch)

All seeded as Open Affinity Tables — no named organizer. The public roster shows them as standard Hosted Tables. Mike handles logistics for all of them.

| Table name | Seed count | Featured? |
| --- | --- | --- |
| JMU Alumni | 12 | ★ Featured |
| Virginia Tech Alumni | 8 | ★ Featured |
| University of Maryland Alumni | 6 | ★ Featured |
| UVA Alumni | 4 | — |
| Georgetown Alumni | 4 | — |
| Healthcare Professionals | 6 | ★ Featured |
| H Tragle 50th Bday | 10 | ★ Featured |
| Lansdowne Crew | 8 | ★ Featured |
| Walter Family Reunion | 8 | ★ Featured |

Total seeded membership: 66 across 9 tables. Provides immediate social-proof gravity at launch.

Display rule (Option A): Public roster shows the count only. Individual member names appear only as real people sign up via the form (with consent). This avoids any name/count mismatch.

Live in code at: src/data/hosted-groups.ts (canonical source). Update counts here weekly as real signups roll in (master Sheet → reflect changes here).

## The "no wrong way" reassurance — three required messages

Mike emphasized these MUST be conveyed clearly, multiple places, to avoid dissuading buyers:

Buy together = seated together. Even without joining a formal group, guests who buy at the same time are seated together automatically.

Hosting and joining are completely optional. A Statesman's Pass works perfectly as a solo ticket.

Don't want to host? Either join an existing affinity/hosted table OR be seated with other distinguished guests in the Statesman's Concierge Area.

These are unified into "Three Ways to Enjoy Your Statesman's Pass" on /hosted-group-tables:

| Option | What it is |
| --- | --- |
| Option 1: Host your own Hosted Table | Bring your group, get the spotlight |
| Option 2: Join an existing Hosted Table | Sit with your tribe (alumni, professional, family) |
| Option 3: Sit independently | Buy solo — seated with other distinguished/honored guests. Buy with friends — seated together automatically, no formal group needed. |

## Operational architecture

### Where the program lives

`/hosted-group-tables` page on countdown250.allamericanball.com — pre-purchase pitch + roster + Create/Join forms (rewritten 2026-04-29)

Eventbrite Statesman thank-you message — post-purchase explainer that points buyers back to the page

### How it works end-to-end (NO BACKEND, MVP-grade)

1. Visitor reads /hosted-group-tables (or links to it from homepage Hosted Tables section)
2. Decides to host OR join OR sit independently
3a. (Host) Buys Statesman's Pass on Eventbrite → returns to page → fills Create form
3b. (Guest) Buys Statesman's Pass on Eventbrite → returns to page → fills Join form (dropdown of existing tables)
3c. (Independent) Just buys Statesman's Pass → no further action needed
4. Eventbrite confirmation email (Statesman tier) explains the program & links back to /hosted-group-tables for anyone who didn't notice the program at purchase time
5. Mike checks the Google Form responses weekly — emails hosts confirmation, updates the public roster (count updates), assigns seating at the event

### Why we DON'T use Eventbrite custom questions

Considered, rejected. Reasons:

Many buyers don't know about the program at purchase time — adding a checkout question they can't answer slows them down

Eventbrite per-ticket-type custom questions are clunky/limited on Mike's plan

The Google Form approach works whether someone decides to host BEFORE or AFTER buying

## The two Google Forms (Mike still needs to build)

### Form #1 — "Create a Hosted Table" (Host signup)

| # | Field | Required |
| --- | --- | --- |
| 1 | Your name (full) | ✅ |
| 2 | Email | ✅ |
| 3 | Phone | optional |
| 4 | Eventbrite order # (verifies Statesman's Pass) | ✅ |
| 5 | Group name (e.g., "Smith Family Reunion") | ✅ |
| 6 | Group theme/description (1 line) | optional |
| 7 | Expected number of guests | optional |
| 8 | May we list you publicly on the website roster? (Yes/No) | ✅ |
| 9 | Anything specific for your stage announcement or table signage? | optional |
| 10 | Anything else we should know? | optional |

### Form #2 — "Join a Hosted Table" (Guest signup)

| # | Field | Required |
| --- | --- | --- |
| 1 | Your name (full) | ✅ |
| 2 | Email | ✅ |
| 3 | Phone | optional |
| 4 | Eventbrite order # (verifies Statesman's Pass) | ✅ |
| 5 | Which group are you joining? (dropdown of all hosted tables + "Other / write-in") | ✅ |
| 6 | May we list your name publicly in the group's roster? (Yes/No) | ✅ |

Operational note on the dropdown: Mike updates the dropdown options manually as new tables are created (~30 sec per addition). For 10–50 hosts over the year, this is ≤5 min/week. Free formRanger add-on can auto-sync from Sheet later if volume justifies.

### Both forms feed into one master Google Sheet

"Hosted Tables — Master" sheet

Columns: Host/Guest name, Email, Phone, Order #, Group, Public-display Y/N, etc.

Public-facing data (Group + Names with consent + count) is what shows on the website

Private data (Email, Order #, Phone) only Mike sees

## Status of the 5 deliverables

| # | Deliverable | Status | Location |
| --- | --- | --- | --- |
| 1 | Full /hosted-group-tables page rewrite | ✅ DONE 2026-04-29 | src/pages/hosted-group-tables.astro |
| 2 | Eventbrite Statesman thank-you message text | ⏳ Drafted in chat — pending paste into Eventbrite admin (see chat history) |  |
| 3 | Host confirmation email | ⏳ Pending — Mike to OK schedule, then Claude drafts |  |
| 4 | Sample host-to-guest invitation email | ⏳ Pending |  |
| 5 | Both Google Form question sets (paste-ready text) | ⏳ Pending — list above is the spec |  |

### Mike's TODO before the program goes live

Create the two Google Forms in Google Forms (use the field specs above)

Replace the placeholder URLs in src/pages/hosted-group-tables.astro:

const CREATE_FORM_URL = "mailto:CountdownAmerica250@gmail.com?subject=...";  // ← replace
   const JOIN_FORM_URL   = "mailto:CountdownAmerica250@gmail.com?subject=...";  // ← replace

Until replaced, both buttons fall back to a prefilled mailto: so visitors can still reach Mike.

Edit the Eventbrite Statesman tier "additional info / thank you" field to include the program description (text drafted in chat history; will be re-delivered as a formal copy doc soon).

Build out the public-display Sheet view (filter master sheet to show only public columns).

## Visual / design conventions established for this program

Section bg: navy (bg-navy, #002868) — primary brand blue, the official "Old Glory Blue" / America 250 color

Feature accent: gold (text-gold, bg-gold)

Body text on navy: white/85 or white/90

Bold value-words on navy: gold (instead of navy)

Headlines on navy: gold or white

CTAs: gold gradient (bg-gradient-to-b from-gold to-[#B8954A]) with navy-dark text — same pattern as the Statesman ticket card's "Host your Own" CTA

Cream cards on navy for content panels (high contrast, easy to read)

Header bar over benefits cards: solid gold bg + navy-dark text (gold-ribbon look)

## Decisions made and rejected (for completeness)

| Topic | Considered | Decision |
| --- | --- | --- |
| Program name | "Hosted Tables Program" / "Party Inside the Party" / "PIP (Party Inside the Party)" | Use both: "Hosted Tables" operationally, "Party Inside the Party" experientially. Drop "PIP." |
| Minimum group size | 6 mandatory cliff vs no minimum | No minimum. 2-tier ladder: any size = Hosted Table; 6+ = Featured. Avoids "I might not qualify, so I won't try" friction. |
| Anchor / seed tables | None vs a few real-host vs many seeded affinity | 9 seeded affinity tables, no named organizer (all "Open"). Mike handles logistics for all of them. |
| Public group display | Hide all info / show counts only / show counts + names | Counts visible from launch. Names visible only when real signups occur (consent gated). |
| Guest→host association | Eventbrite custom question / Google Form on the page / mailto: | Google Form on the page. Eventbrite limitations + risk of confusing buyers killed option 1. |
| AI Fanatics seed table | Include / exclude | Excluded — lower obvious affinity for this event's positioning. |

## Audit guardrails (for any future Claude session)

Run before every push:

python scripts/audit_assets.py

Six checks: (1) image existence, (2) internal route resolution, (3) in-page anchor resolution, (4) duplicate IDs, (5) carousel dot/slide match, (6) dead/missing named imports (added 2026-04-29 after a deploy break caused by a renamed export).

All 6 must pass before push. Both hostedTables array updates and any export renames are covered by Check #6.